## Semester Project Report
SSC Budget and Timeline Form - Semester Project Report
The SSC Budget and Timeline Form - Semester Project Report must be completed and submitted every semester regarless of the original application type. This form requires a list of updated project timelines and milestones and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | A student-driven recensus of the Trelease Woods Forest Dynamics plot
| Original Award Date (or Semester/Year)*: | 2022-12-01 | (<*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.)
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 72721
| Total Expenses This Period**: | 72717.38 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 0 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Expected Date of Project Completion: | 2025-01-12
| Date of This Application Submission: | 02/18/2026
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the progress you have made on the project since your last semester report. Include start and end dates and % complete). Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the progress of this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Milestone 1: Completion of the full census of all woody individuals in Trelease Woods |  |  | 2023-08-01 | 2025-01-12 | 70%
Milestone 2: Training of undergrad students in Datascience using Trelease dataset |  |  | 2023-08-01 | 2025-01-12 | 100%
Milestone 3: Completion of census data quality checks |  |  | 2023-12-01 | 2025-01-12 | 60%
Impact 1: Completion of the Trelease Woods carbon budget based on initial census data |  |  | 2023-08-01 | 2025-05-01 | 100%
Impact 2: Integration and use of Trelease census data into undergraduate ecology classes |  |  | 2023-08-01 | 2025-05-01 | 100%
EXPENSES
List all expenditures from this award made since the last submitted semester project report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 0
Publicity & Communication
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
Graduate research Assistant Fall 2023 |  |  |  | 14059.95
Graduate research Assistant Fall 2024 |  |  |  | 13248.73
Graduate research Assistant Fall 2025 |  |  |  | 13940.55
Undergraduate hourly workers - summer 2024 |  |  |  | 3857
Undergraduate hourly workers - summer 2025 |  |  |  | 12347.36
Undergraduate hourly workers Fall 2025 |  |  |  | 12080
Benefits - RA and hourly workers |  |  |  | 2020.59
0
0
0
Personnel & Wages Subtotal |  |  |  | 71554.18
General Supplies & Other
Item |  |  |  | Total Spent
Numbered tree tags |  |  |  |  | 14
Numbered tree tags |  |  |  |  | 290
Tree Paint |  |  |  |  | 662
Powerbank - to charge ipads in the field |  |  |  |  | 111.32
Digital calipers to measure small trees |  |  |  |  | 46.78
Caliper batteries |  |  |  |  | 39.1
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 1163.2
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 72717.38