## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Biomass boiler upgrades to ash handling system
Total Amount Requested from SSC: | 12156.61
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Issue Purchase Order for upgrade parts | 2 |  | 2022-06-15
Manufacturing Time (dependent on queue) | 10 |  | 2022-09-01
Shipment from Germany to Canada then US | 5 |  | 2022-10-07
Installation | 2 |  | 2023-06-01
Start of 2023/24 Heating Season and Testing |  |  | 2023-09-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Parts from Heizomat Germany | 9996.45 | 1 | 11794.75
F&S Electricains | 72.51 | 16 | 1343
F&S Electrical supplies for installation |  | 1 | 501
Misc hardware / sheet metal for installation | 1897 | 1 | 1897
0
0
0
0
0
0
|  | Subtotal | 15535.75
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
Labor Provided by Energy Farm for Installation(hours) | 0 | 16 | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 15535.75
End of Application