## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Intelligent Mobile Sensing Unit for Building Energy Efficiency
Total Amount Requested from SSC: | 35198.52
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Robot procurement | 2 weeks |  | 2022-09-15
Procurement of a camera and sensors that read indoor environmental parameters (e.g., temperature, humditiy) | 2 weeks |  | 2022-09-15
Planning of a controlled experiment (e.g., experimental set-up, IRB appoval) that uses a mobile camera to collect data for thermal discomfort prediction modeling | 8 weeks |  | 2022-09-01
Materials procurement for the thermal discomfort prediciton experiement (data collection) | 2 weeks |  | 2022-09-01
Experiment to collect data for thermal discomfort prediction modeling | 7 weeks |  | 2022-10-15
Computational experiments for thermal discomfort prediction modeling | 8 weeks |  | 2022-12-31
Robot assembly, engineering design and programming for autonomous navigation | 8 weeks |  | 2022-10-15
Intelligent system configuration and deployment in Hydro Building | 16 weeks |  | 2023-04-15
Computational experiments to optimize building energy consumption and occupant comfort, including validation | 8 weeks |  | 2023-07-31
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Mobile robot | 5000 | 1 | 5000
Research Packages (autonomy navigation, LiDARS) | 8500 | 1 | 8500
Robot accessories (e.g., batteries, charging stations, sensors, cameras) | 6000 | 1 | 6000
Portable heaters/cooling devices and sensors/technologies for controlled expreriments | 1500 | 1 | 1500
Computational module (e.g., CPU/GPU) | 4000 | 1 | 4000
0
0
0
0
0
0
|  | Subtotal | 25000
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Research Assistant (25% appointment, 1 semester) | 9198.52 | 1 | 9198.52
0
0
0
0
0
0
0
0
0
|  | Subtotal | 9198.52
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Incentives (Phase: Thermal discomfort modeling experiment) | 500 | 1 | 500
Incentives (Phase: System deployment in Hydro) | 500 | 1 | 500
0
0
0
0
0
0
0
0
|  | Subtotal | 1000
|  | TOTAL BUDGET | 35198.52
End of Application