## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Purchase and Install new Eco-Counters
Total Amount Requested from SSC: | 60000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Work Order to purchase and install Eco-Counters | Less than a week after approval |  | 2022-05-31
Call for quotes from Eco-Counter | 4 weeks after approval |  | 2022-06-30
Approval of locations | 2 weeks |  | 2022-06-30
Purchase Order to purchase the Eco-Counters | 3-4 weeks after Quote is received |  | 2022-07-31
Receiving the Eco-Counters | 6-8 weeks of delivery time |  | 2022-09-30
Installation of Eco-Counters | 8-12 weeks (depending on crew availability) |  | 2022-12-20
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Purchase of Eco-Counters | 7000 | 6 | 42000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 42000
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
Installation cost (3 locations) | 6000 | 3 | 18000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 18000
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 60000
End of Application