## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Identifying the campus benefits of a large-scale prairie experiment
Total Amount Requested from SSC: | 75000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Advertise for students for summer sample | 4 weeks |  | 2021-02-15
Preparation and training for SU 21 sampling | 8 weeks |  | 2021-05-15
Student led sampling of plant bee and soils | 12 weeks |  | 2021-08-15
Data processing and handling | 16 weeks |  | 2022-04-01
Preparation and training for SU 22 sampling | 8 weeks |  | 2022-05-15
Student led sampling of plant bee and soils | 12 weeks |  | 2022-08-15
Data processing and handling | 16 weeks |  | 2023-04-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Site maintenance SU 21 (e.g. mowing, burning, mapping) | 5000 | 1 | 5000
Site maintenance SU 22 (e.g. mowing, burning, mapping) | 5000 | 1 | 5000
0
0
0
0
0
0
0
0
|  | Subtotal | 10000
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Student Workers in Summer 21 - flat $5000 stipend | 5000 | 3 | 15000
student Workers in Summer 22- flat $5000 stipend | 5000 | 3 | 15000
Student Workers in FA 21 ( $12/h for up to 15 h/week ) | 2500 | 1 | 2500
Student Workers in SP 22( $12/h for up to 15 h/week ) | 2500 | 2 | 5000
Student Workers in FA 22 ( $12/h for up to 15 h/week ) | 2500 | 1 | 2500
Student Workers in FA 21 ( $12/h for up to 15 h/week ) | 2500 | 2 | 5000
Student Workers in SP 23 ( $12/h for up to 15 h/week ) | 2500 | 2 | 5000
Student Workers in FA 22 ( $12/h for up to 15 h/week ) | 2500 | 2 | 5000
|  | Subtotal | 55000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Research Budget Per Summer Student (SU 21) | 1000 | 3 | 3000
Research Budget Per Summer Student (SU 22) | 1000 | 3 | 3000
drying time in large soyFACE drying ovens SU 21 | 2000 | 1 | 2000
drying time in large soyFACE ovens SU 22 | 2000 | 1 | 2000
0
0
0
0
0
0
|  | Subtotal | 10000
|  | TOTAL BUDGET | 75000
End of Application