## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: |  | Joint Pollinator Garden-Composting System to Offset Environmental Impact & Reinforce Responsible Stewardship in Research
Total Amount Requested from SSC: |  | 32157
Amount Requested as: |  | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task |  | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Composters ordered, composting in Chemistry and IB begins |  | 2 weeks |  | 2020-04-01
Monthly meetings with student volunteers, cultural houses begin |  | continuous |  | N/A
Locate and excavation of Davenport part #2 and Vivarium begins |  | 4 weeks |  | 2020-04-30
Rain barrels ordered and installed |  | 4 weeks |  | 2020-04-30
Davenport and Vivarium plants ordered and installed |  | 6 weeks (from ordering to installation) |  | 2020-05-01
Outreach to 4H |  | N/A |  | 2020-05-01
First microfaunal surveys begin |  | continuous May-November, over two years |  | 2021-05-25
Signage in place, gardens added to website |  | 4 weeks( from ordering to installation) |  | 2020-06-30
Spring 2020 semesterly report | submission | N/A |  | 2020-07-01
Human biology guidance submission (reporting on garden) |  | 39 weeks |  | 2020-09-30
Fall 2020 semesterly report submission |  | N/A |  | 2021-01-20
Composters ordered, composting in IGB begins |  | 2 weeks |  | 2021-04-01
Outreach via Extension office, and USD116 schools |  | 4 weeks |  | 2021-04-30
IGB Rain barrels ordered and installed |  | 4 weeks |  | 2021-04-30
IGB plants ordered and installed |  | 6 weeks (from ordering to installation) |  | 2021-05-01
IGB microfaunal surveys begin |  | continuous May-November, over two years |  | 2022-05-25
Signage in place, garden added to website |  | 4 weeks( from ordering to installation |  | 2021-06-30
Spring 2021 semesterly report submission |  | N/A |  | 2021-07-01
Human Biology guidance featuring gardens published |  | 50 weeks from submission |  | 2021-08-31
Promotion of gardens and publication through Illinois News, journal |  | N/A |  | 2021-08-31
Final report |  | 91 weeks |  | 2021-09-30
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item |  | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Plants (prairienursery.com) |  | 4.99 | 1280 | 6387.2
Rain barrels |  | 120 | 5 | 600
Gardening supplies (e.g. Shovels, gloves, watering cans, leaf litter bags) |  | 420 | 1 | 420
Soil (cubic yard) |  | 150 | 6 | 900
Mulch (cubic yard) |  | 150 | 5 | 750
composters (Bokashi indoor composters) |  | 60 | 10 | 600
0
0
0
|  |  | Subtotal | 9657.2
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
Personnel & Wages
Student labour for set up (per hour, per student, 2 students) |  | 15 | 200 | 3000
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 3000
Project Budget per F&S
Rain barrel pipe construction and installation (per rain barrel) |  | 1800 | 5 | 9000
Ground preparation and soil installation (IGB, Vivarium, Davenport) |  | 6000 | 1 | 6000
Sign creation and (per sign) |  | 900 | 4 | 3600
0
0
0
0
0
0
0
|  |  | Subtotal | 18600
General Supplies & Other
Greenhouse space and soil (for ~1280 plants, for 2 months) |  | 900 | 1 | 900
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 900
|  |  | TOTAL BUDGET | 32157.2
End of Application