## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Restoration of Low Mow Area at Orchard Downs Housing Faculity
Total Amount Requested from SSC: | 8000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Plot Survey and Results | 3 weeks |  | October 1st, 2023
Research and Management Plan | 3 weeks |  | November 1st, 2023
Manual Removals | 10 weeks |  | May 1st, 2024
Seeding and Planting | 2 weeks |  | May 1st, 2024
Start Greenhousing | 3 weeks |  | February 17th, 2024
Transplant Plugs | 3 weeks |  | March 30th, 2024
Manual Removals | 10 weeks |  | November 1st, 2024
Seeding | 3 weeks |  | October 15th, 2024
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs |  |  |  | Notes
Water |  |  |  | estimate of $7.10 per 1,000 gallons
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
Social Medias/Website | 0 |  | 0
Misc. (posters, flyers, etc.) | 50 | 1 | 50
0
0
0
0
0
0
0
0
|  | Subtotal | 50
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
Mowing 1 time per year | 0 | 2 | 0 | Facility and Services will do this for free once a year
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Greenhouse space | 550 | 2 | 1100 | Estimation based on 2 (5 ft by 4ft) = $500 per semester
Native plant seeds/ plugs | 1500 | 2 | 3000
Garden Trowel | 7 | 15 | 105
Hand Weeder | 7 | 10 | 70
Loppers | 20 | 10 | 200
Land Augur Drill Bit and Cordless Drill | 45 | 2 | 90
Herbicide (Chemicals, spray backpack, mixing tools) | 200 | 1 | 200
Truck Rental for moving plants
Yard bags (bundle of 4) | 5 | 5 | 25
Yard Plaque or Large Engraved Rock
Money for unknown misc. items/ possible problems (die off of plants, miscalculation of prices, community events for the plot) | 1500 | 1 | 1500
|  | Subtotal | 6290
|  | TOTAL BUDGET | 6340
End of Application