## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | The Hip-Hop Xpress
Total Amount Requested from SSC: | 119744.7
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Installation of Full Exterior Vinyl Wrap of Hip Hop Xpress Graphics | 2 Weeks |  | 2019-01-17
Schematic Design of Bus Interior | 2 Weeks |  | 2019-01-31
Demo Existing Bus Seats & Recycle Components | 2 Weeks |  | 2019-02-14
Design Development of Bus Interior | 2 Weeks |  | 2019-02-28
Install SunPower Felxible Solar Panels | 1 Week |  | 2019-03-06
Prototype Various Interior Design Components | 3 Weeks |  | 2019-03-27
Complete Fabrication/ Construction Drawings | 2 Weeks |  | 2019-04-10
Install Electrical Components & New Wiring | 2 Weeks |  | 2019-04-24
Fabricate All Interior Components (Recording Studio, Seating, etc.) | 3 Weeks |  | 2019-05-15
Paint & Install all Interior Components | 2 Weeks |  | 2019-05-29
Punch List & Systems Check | 3 Weeks |  | 2019-06-19
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
200 Watt 12 V Fleixble Solar Panel w/ storage system | 600 | 21 | 12600
720 Watt Portable Solar Generator | 999.9 | 2 | 1999.8
Recording Studio (build-out, sound proofing, wiring) | 20000 | 1 | 20000
Furniture, Fixtures, & Equipment (FF&E) sound system not included | 30000 | 1 | 30000
Prototypes (deployable & fixture furniture) | 3000 | 1 | 3000
0
0
0
0
0
|  | Subtotal | 67599.8
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
F&S Electricians | 5000 | 1 | 5000
CNC & 6-axis Robotic Arm Machine Time | 5000 | 1 | 5000
Student Hourly Labor | 15 | 960 | 14400
Architecture Faculty Stipend - Spring 19 Service in Excess (SIE) | 9250 | 1 | 9250
Architecture Faculty Stipend - Summer Stipend | 9250 | 1 | 9250
0
0
0
0
0
|  | Subtotal | 42900
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Renewable Energy Science Kits for School & Community Programming | 324.99 | 10 | 3249.9
Horizon Energy Box Kit for School & Community Programming | 1199 | 5 | 5995
0
0
0
0
0
0
0
0
|  | Subtotal | 9244.9
|  | TOTAL BUDGET | 119744.7
End of Application