## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Valorizing Archived Soils: Changes in the Land, Carbon, and Nutrients in the 20th century
Total Amount Requested from SSC: | 79957.582
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Moving soil samples (~2,000) from campus farm building to main campus | 8 |  | April 2020 - June 2020
Inventorying, labeling, restoring samples | 12 |  | July 2020 - September 2020
Analyzing soils for carbon and nutrients | 20 |  | October 2020 - February 2021
Project website | 8 |  | January 2021 - February 2021
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
|  | Subtotal | 0
Publicity & Communication
Initiation symposium and panel | 400 | 1 | 400
Website development | 1200 | 1 | 1200
Graphic artist for website, outreach | 500 | 1 | 500
Travel to Chicago outreach events (van rental, mileage) | 220 | 3 | 660
Good Food Expo booth rental | 450 | 2 | 900
Travel to Springfield, IL for NLRS symposium | 150 | 2 | 300
Travel (grad student) to national conferrence | 1400 | 1 | 1400
|  | Subtotal | 5360
Personnel & Wages
Undegraduate students | 3100 | 4 | 12400
Graduate student, 50% FTE (12 mo rate) | 24490.2 | 1.5 | 36735.3
co-PI Christianson, salary and benefits | 5762.282 | 1 | 5762.282
|  | Subtotal | 54897.582
Project Budget per F&S
|  | Subtotal | 0
General Supplies & Other
Shelving | 600 | 20 | 12000
Lifetime labels | 15 | 20 | 300
Inventory Tables | 400 | 1 | 400
Sample analysis (i.e. total carbon) | 10 | 400 | 4000
Resample collection | 200 | 15 | 3000
0
0
0
0
0
|  | Subtotal | 19700
|  | TOTAL BUDGET | 79957.582
End of Application