## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | An Energy Saving Demonstration for Remodeling Old Structures
Total Amount Requested from SSC: | 19000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
order 4 doors and 17 windows | delivery 45 days after order placement |  | Order immediately once funding is approved
Install 4 doors and 17 windows | 6 weeks after materials are received |  | October 1 2019
Install new weatherstripping around overhead doors | 12 weeks |  | October 1 2019
Seal around building joints and wall penetrations | 12 weeks |  | October 1 2019
Seal around other areas as identified | 12 weeks |  | October 1 2019
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
insulated walk through doors | 2115.83 | 4 | 8463.32
insulated, low-E argon filled windows | 562.85 | 17 | 9568.45
Weatherstripping | 650 | 1 | 650
0
0
0
0
0
0
0
|  | Subtotal | 18681.77
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
caulking | 6.98 | 10 | 69.8
Door and Window foam sealant | 6.49 | 10 | 64.9
General use foam sealant | 4.49 | 10 | 44.9
unanticipated materials | 138.63 | 1 | 138.63
0
0
0
0
0
0
|  | Subtotal | 318.23
|  | TOTAL BUDGET | 19000
End of Application