## SSC Step II Application
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Campus Instructional Facility (College of Engineering)
Total Amount Requested from SSC: | 375000 | *$250,000 previously funded, $125,000 fund request for Spring 2018
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  |  | Estimated Completion Date
Drilling Testing/Monitoring Hole | 2 weeks |  |  | 2018-12-17
Monitoring | Ongoing |  |  | Ongoing
Install perimeter fence, strip topsoil (including signage for publicity) | 1 week |  |  | 2019-07-12
Drill wellheads, install vertical heat exchanges | 6 weeks |  |  | 2019-08-23
Install wellfield piping, vault, manifold | 3 weeks |  |  | 2019-09-13
App development, roll out of communication plan | Ongoing |  |  | Ongoing
Trench/install manifold piping back to building | 3 weeks |  |  | 2019-10-04
Restoration: sidewalks, landscape | 4 weeks |  |  | 2019-11-01
Remove fencing, demobilize | 1 week |  |  | 2019-11-08
HVAC Commissioning | Milestone |  |  | Fall, 2020
Substantial Completion | Milestone |  |  | Winter, 2020
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total SSC Request | Total Geothermal Exchange Project
|  |  | 376000 | 3542372.9
Equipment & Construction Costs
Geothermal Implementation (funded by SSC and other sources)
Geothermal Wells, Vault, Wellfield Piping | 23.75 | 18000 | 44351.4339 | 427500
Geothermal Heat Pump | 2975 | 140 | 43210.2274 | 416500
Geothermal Water Storage Tanks | 9000 | 2 | 1867.4288 | 18000
Secondary set of pipe risers with insulation, controls | 271575 | 1 | 28174.832 | 271575
Radiant Heating Panels - Lower Level | 41.6 | 7395 | 31915.6031 | 307632
Radiant Heating Panels - Level 1 | 41.6 | 6690 | 28872.9391 | 278304
Radiant Heating Panels - Level 2 | 41.6 | 9340 | 40309.903 | 388544
Radiant Heating Panels - Level 3 | 41.6 | 9783 | 42221.8181 | 406972.8
Radiant Heating Panels - Level 4 | 41.6 | 10012 | 43210.1444 | 416499.2
Earthwork: silt fence, sidewalk demo, topsoil, stone | 1.7 | 73842 | 13023.3862 | 125531.4
Site Concrete: 8" thick sidewalks, broom finish | 9.5 | 13828 | 13628.7028 | 131366
Landscape: respread topsoil, fine grade, sod restoration | 0.8 | 73842 | 6128.6523 | 59073.6
Architectural Design, Engineering and Commissioning | Per MEP Engineer |  | 5239.1752 | 50500
Contingency | Per General Contractor |  | 16845.7536 | 162374.9
|  | Subtotal | 359000 | 3460372.9
Publicity & Communication
Publicity & Communication, Studen Engagement
Funded by SSC
Digital App: Development and Deployment of a student-focused digital application for geothermal exchange energy monitoring | 8000 | 1 | 8000 | 8000
Digital App: Development and Deployment of a student-focused digital application for Classroom information and Scheduling | 2000 | 1 | 2000 | 2000
SSC Project Digital Communications: communication of SSC's involvement and contribution to the geothermal exchange project on the digital displays at the Campus Instructional Facility | 500 | 12 | 6000 | 6000
Funded by College Of Engineering
Geothermal Exploration Digital App: Development and Deployment of an App for Geothermal Monitoring Hole by Computer Science faculty and Students | 0 | 1 | 0 | 0
SECS: Engament with SECS Sustainabiltiy Sub-committee | 0 | 1 | 0 | 0
Independent Study for Architecture Students: P3 Project and CIF Geothermal Exchange | 0 | 1 | 0 | 0
Seminar: Advances in Geothermal Heat Pump (GHP) systems: Fiber optic based underground Distributed Temperature Sensing (DTS) & Underground Thermal Energy Storage (UTES)systems (Lunch and Space Provided) | 500 | 1 | 500 | 500
iSEE Student Intern for iSEE Communication: P3 Project and CIF Geothermal Exchange | 0 | 1 | 0 | 0
Geothermal Exchange Class Visit at the Construction Site (Planning) | 0 | 1 | 0 | 0
Enginering Open House (Planning) | 500 | 1 | 500 | 500
|  | Subtotal | 17000 | 17000
Personnel & Wages
Personnel (funded by other sources)
Associate Dean of Facilities and Capital Planning, College of Engineering (Dr. Liang Y. Liu) |  |  | 0 | 0
Director of Facilities, College of Engineering (Qu Kim) |  |  | 0 | 0
Senior Planner, Facilities and Services (F&S) (Doug Reddington) |  |  | 0 | 0
Associate Geologist, Prairie Research Institute (PRI) (Dr. Andrew Stumpf) |  |  | 0 | 0
Hydrogeology and Geophysics (Dr. Yu-Feng Lin) |  |  | 0 | 0
Other Development Team members |  |  | 0 | 0
|  | Subtotal | 0 | 0
Project Budget per F&S
Drilling Testing/Monitoring Hole (tentatively funded by the Carbon Credit Sale Fund)
Metal Fence: 12 days of Installation, Maintenance, and dissemblance of Metal Fence around the Testing Drilling Hole on the Bardeen Quad | 500 | 12 | 0 | 6000
Vacuum Truck: 12 days of removal of drilling fluids and drill cuttings by F&S vacuum truck | 900 | 12 | 0 | 10800
Site Restoration: restoration/redesign of the ground and concrete path on the Bardeen Quad | 10000 | 1 | 0 | 10000
|  | Subtotal | 0 | 26800
General Supplies & Other
Drilling Testing/Monitoring Hole (tentative funded by the Carbon Credit Sale Fund)
Test Hole Drilling: 10 days of one test hole drilling on the Badeen Quad for soil testing | 2950 | 10 | 0 | 29500
Borehold Geophysics: 1 day of collecting logs of soil properties for well bore/borefield modeling | 2000 | 1 | 0 | 2000
U-bend PVC pipe (1000-feet) for DTRT testing | 360 | 1 | 0 | 360
Fiber-Optic Cable: fiber-optic cable to measure ambient temperature in borefield (cost of cable, and installation in test hole); steel-wrapped cable required to protect fiber optics from “darkening” when in the ground for more than 20 years | 3000 | 1 | 0 | 3000
Installation of underground utilities box to store fiber optic cable; small above-ground plastic box/above-ground structure not allowed by F&S at the site | 3340 | 1 | 0 | 3340
|  | Subtotal | 0 | 38200
|  | TOTAL BUDGET | 376000 | 3542372.9 | 10.61%
|  |  | Total SSC Request | Total Geothermal Exchange Project
End of Application