## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Krannert Art Museum-East Gallery Lighting System Replacement
Total Amount Requested from SSC: | 75000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
East Gallery Renovation w/lighting system replacement
PSC Selection Phase | 4 |  | 2019-04-03
Design Duration | 20 |  | 2019-10-16
Bidding and Negotiating Phase | 10.5 |  | 2020-02-04
Construction Phase | 21 |  | 2020-08-27
Please note that the lighting system replacement is a component of a larger renovation project.
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Labor |  |  | 21533
Lighting Control panel | 2 | 20863 | 41726
Tracks, wall washers, track fixtures |  |  | 270352
Price above consist of: |  |  | 0
Track - 795 feet |  |  | 0
Track fixtures - 295 |  |  | 0
Wall washers - 96 |  |  | 0
Recessed emergency light - 4 |  |  | 0
0
0
|  | Subtotal | 333611
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 333611
End of Application