## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | South-Farm Nitrate Monitoring Station
Total Amount Requested from SSC: | 103227.91
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Begin search for undergraduate employees/interns | February, 2019 (8 weeks) |  | 10 April, 2019
Order and receive water quality and flow instruments | February, 2019 (4-6 weeks delivery) |  | 5 April, 2019
Install instruments and trouble shoot | April, 2019 (3 weeks) |  | 1 May, 2019
Customize online data dashboard | May, 2019 (3 weeks) |  | 7 June, 2019
Discussions with faculty about availability of collected data for use in the classroom | June, 2019 (12 weeks) |  | 30 August, 2019
Evaluate social media options and general communications | June, 2019 (28 weeks) |  | 18 December, 2019
Final report | January, 2020 (2 weeks) |  | 15 January, 2020
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
YSI Nitrate/Multi Sonde | 17136 | 2 | 34272
YSI Remote Communication | 2615 | 2 | 5230
ISCO LaserFlow™ Non-contact Velocity Sensor | 14347.2 | 1 | 14347.2
0
0
0
0
0
0
0
|  | Subtotal | 53849.2
Publicity & Communication
Web hosting and data storage | 1147 | 2 | 2294
Semiannual newsletter or fact sheet | 75 | 2 | 150
0
0
0
0
0
0
0
0
|  | Subtotal | 2444
Personnel & Wages
Field Technician - site installation, student training, data management | 17334 | 1 | 17334
Lab Technician | 3394.575 | 1 | 3394.575
Undergraduate Hourly - Data collection and analysis | 10414.56 | 1 | 10414.56
Faculty PI (management) | 6283.575 | 1 | 6283.575
0
0
0
0
0
0
|  | Subtotal | 37426.71
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Sonde Maintenance | 1000 | 2 | 2000
Mounting supplies, batteries, and solar panel accessories | 1500 | 2 | 3000
Contractual: Water quality analysis via laboratory | 14.5 | 104 | 1508
Contractual: Stream survey to develop cross-sectional flow area | 3000 | 1 | 3000
0
0
0
0
0
0
|  | Subtotal | 9508
|  | TOTAL BUDGET | 103227.91
End of Application