## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Vision Zero for UI
Total Amount Requested from SSC: | 28800
Amount Requested as: |  | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Develop surveys and obtain permission from campus to distribute them and do focus groups | 6 |  | 2019-09-30
Collect Crash Data | 8 |  | 2029-11-30
Distribute the survey and collect feedback from focus groups | 8 |  | 2020-01-30
Analyze data and get feedback from focus group meetings to identify critical safety areas | 16 |  | 2020-05-30
Discuss feasible solutions with the stackholders | 6 |  | 2020-07-15
Prepare a final report | 4 |  | 2020-08-15
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Research Assistant salary and fringe benefits | 2400 | 12 months | 28800
0
0
0
0
0
0
0
0
0
|  | Subtotal | 28800
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 28800
End of Application