## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: |  | Geothermal exchange for greenhouses at UIUC Energy Farm
Total Amount Requested from SSC: |  | 87000 | Total Amount Allocated: | 132550
Date of Submission: |  | 2023-08-22
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task |  | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Engineering design and project planning |  | 6 |  | completed
Drill boreholes and install geothermal loops (Skinner and Durbin) |  | 3 |  | completed
Purchase geothermal heat pump (ClimateMaster) |  | 1 |  | completed
Complete trenching to bring geothermal loops into building |  | 1 |  | Fall 2023*
Install heat and cooling system piping |  | 2 |  | Fall 2023*
Install new electrical lines |  | 2 |  | Fall 2023*
Install control center and IT communications |  | 0.5 |  | Fall 2023*
Install geothermal heat pump |  | 0.5 |  | Fall 2023*
* See F&S cost breakdown (uploaded with worksheet)
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item |  | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
| Olympic Construction - general construction |  |  | 3219
| DUCE Construction - rework concrete floor |  |  | 4900
| Prairie Restorations - grading and seeding |  |  | 4000
| Krut's Electric - electric rework |  |  | 11892
| BPI Testing - TAB |  |  | 900
| Champaign A&K Insulation - Mechanical Insulation |  |  | 4500
| 6 - SHEETMETAL (F&S) - Ductwork |  |  | 5065.92
| 23 - PIPEFITTERS (F&S) - Piping |  |  | 52406
0
0
|  |  | Subtotal | 86882.92
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
|  |  | TOTAL BUDGET | 86882.92
End of Application