# *From time to time unforeseen challenges or opportunities can affect the planned budget, timeline, or overall goals of a project funded by the Student Sustainability Committee. Past examples of these situations include projects coming in under budget but having additional opportunities available, or inclement weather delaying the planting of agriculture projects.*

# *Below please include a brief project summary and your requested changes. Attach additional documents as needed. If you have any questions, please contact the Student Sustainability Committee at sustainability-committee@illinois.edu.*

# General Information

**Project Name:** Illinois Sustainable Food Project – Tortilla Expansion

**Total Amount Requested from SSC:** $135,000

**Date of Scope Change Submission:** 2/1/2022

# Contact Information

Project Lead Name: Brian Jacobson

Scope Change Applicant Name (if different than Project Lead):

Unit/Department: Food Science & Human Nutrition

Email Address: bjacobs3@illinois.edu

# Project Information

Please provide a brief background of the project, the goals, and the desired outcomes:

The purpose of this project is to use underutilized corn grown in research programs on campus for producing tortillas and tortilla chips for the campus dining halls. This is an expansion on existing ISFP projects.

Please provide a brief summary of how students will be involved in the project’s changes:

No change from original

Mark the components for which you are applying to change. (Mark all that apply.)

[ ] Overall goals

[ ] Budget

[X] Timeline

* Original Timeline:
* New Timeline: Final equipment arrival and invoices paid by 5/15/2023

[ ] Other

Please provide a brief summary of your requested scope change. How is your request different from your original plan? Please explain the reason for the proposed changes.

I request only a time extension to complete equipment procurements.

Additional comments (Optional)

Any additional comments/relevant information for the project proposal