## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Student-led Census of the Trelease Woods Forest Dynamics Plot
Total Amount Requested from SSC: | 72866.53
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Purchase of census materials | 4 weeks |  | 06/30/2018
Recruitment of undergrad student census workers | 12 weeks |  | 08/14/2018
Student orientation and training | 1 week |  | 08/21/2018
Development of project website | 6 weeks |  | 10/15/2018
Completion of first 12 ha of census | 12 weeks |  | 2018-11-09
Completion of the next 6 ha of census | 5 weeks |  | 2019-01-05
Break for final exams | 1 week |  | 05/14/2019
Completion of last 6 ha of census | 3 weeks |  | 2019-07-06
Complete data cleaning and review of problem trees | 4 weeks |  | 2019-07-07
Release final version of census data | NA |  | 2019-07-07
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
TruPulse 360R laser rangefinder/hyposmeter | 1600 | 3 | 4800
Forestry Suppliers 283D/5M tree diameter tape | 38.25 | 9 | 344.25
Forestry Suppliers 283D/10M tree diameter tape | 44.95 | 3 | 134.85
SPI Plastic dial caliper 31-413-5 to measure small trees | 38.65 | 6 | 231.9
Suunto MC2 Navigator Compass | 45 | 6 | 270
TruPulse 360R foliage filter | 63.95 | 3 | 191.85
Trupulse mounting staff and bracket | 192 | 3 | 576
|  | Subtotal | 6548.85
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
11 month Graduate Student Research Assistant | 26026 | 1 | 26026
Hourly wages for undergrad field crew leaders at $10 per hour | 10 | 2500 | 25000
0
0
0
0
0
0
0
0
|  | Subtotal | 51026
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Nelson Paint Nel-script tree marking paint | 222.24 | 12 | 2666.88
Forestry Suppliers vinyl flagging tape (temporary tree marker) | 2.95 | 24 | 70.8
National Band and Tag tree tags | 0.089 | 40000 | 3560
Simpson Swan Secure 3" stainless steel nails 1800 pack | 170.24 | 23 | 3915
1" PVC tubing to mark corners of 10 x 10 m quadrats | 3.33 | 480 | 1598.4
Monthly vehicle pool minvan rental for travel to Trelease | 450 | 7 | 3150
Forestry suppliers vinyl tree tape to tag small trees (rolls) | 2.25 | 36 | 81
Gasoline for minivan (4 gallons/week) for 24 weeks | 2.6 | 96 | 249.6
0
0
|  | Subtotal | 15291.68
|  | TOTAL BUDGET | 72866.53
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
NA
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
GHG of this project is associated with CO2 emissions from driving from campus to Trelease Woods. We estimate a maximum useage of 4 gallons per week x 24 weeks = 1862lb CO2
End of Application