## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | U16102 – Business Instructional Facility (BIF) 4TH Floor Office Addition – Photovoltaic (PV) Solar Panels
Total Amount Requested from SSC: | 157340
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
50% CD Submission |  |  | 2017-05-17
95% CD Submission |  |  | 2017-07-28
100% CD/Out to Bid |  |  | 2017-09-01
Bid openings |  |  | 10/4/2017 - 10/6/17
Construction start | 72 |  | 2018-01-05
Substantial completion |  |  | 2019-05-24
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
New PV System - (44) x 285W Solar World PV Modules + Inverters | 40960 | 1 | 40960
(excludes batteries/ PV Credit) |  |  | 0
PB: N4000AA - 20A | 90 | 2 | 180
(2) 3/4" RMC Raceways + Wiring 3#10 + 1#10 | 7 | 600 | 4200
New Cat 6 Cable | 2000 | 1 | 2000
Extend 42"h Parapet | 250 | 200 | (withdrawn)
0
0
0
0
|  | Subtotal | 47340
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Phasing/Premium Time/Escalation |  |  | 14000
Bonds/Insurance/Profit |  |  | 13000
Design Contingencies |  |  | 9000
General Contidions |  |  | 24000
0
0
0
0
0
0
|  | Subtotal | 60000
|  | TOTAL BUDGET | 107340
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
N/A
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
Per the provided PVWatts calculations, the additional PV panels will save 15,450 kWh per year. At the University utility rates of $0.0859 per kWh, the new PV would save $1,327 per year. At 1.672 CO2lb/kWh, the new PV panels would save 25,832 lbs CO2.
End of Application