## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | "Roly Poly" Bicycle Registration and RFID Tracking Program
Total Amount Requested from SSC: | 25207
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
To implement the project, we will spend a little over a year and a half working on building the hardware part of the project. Assuming a start date of January 5th, 2017, we hope to have the project assembled by the end of July 2018. The software part of the project will take an estimated year and a half. These tasks will be completed simultaneously. We will mount the equipment in August 2018 and contact local buisnesses for the rewards system begining in June of 2018. Distribution of the tags will begin after the tags are assembled and the equipment is mounted in August. The major milestones of the project are: the completion of the instrument enclosure, which will be done by July 30, 2018; the completion of the software, which will be done by August 31, 2018; and the completion of the website and database, which will be done by March 1, 2018.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Create Database | 12 |  | 2017-03-30
Antenna Research and Development | 17 |  | 2017-05-01
Design Tag Mounting | 4 |  | 2017-05-30
Power | 30 |  | 2017-11-30
Create Website | 52 |  | 2018-03-01
Assemble Circuit Boards | 20 |  | 2018-04-30
Assemble Instrument Enclosure | 13 |  | 2018-07-30
Assemble RFID Tags | 13 |  | 2018-08-30
Link Database to System | 26 |  | 2018-08-31
Mount Instrument Enclosures | 4 |  | 2018-08-31
Contact Businesses | 22 |  | 2018-10-31
Distribution | Ongoing
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
RFID Antenna | 400 | 10 | 4000
RFID Interogator Module | 300 | 10 | 3000
WiFi Module | 10.25 | 10 | 102.5
RFID Tag | 0.5 | 1000 | 500
Tag Mounting | 1.25 | 1000 | 1250
Printed Circuit Board | 30 | 10 | 300
Instrument Enclosure | 150 | 10 | 1500
Smoothing Capacitor | 10 | 10 | 100
Transformer | 15 | 10 | 150
Voltage Regulator | 3 | 10 | 30
Rectifier | 1 | 10 | 10
Battery | 110 | 10 | 1100
Battery Charger with Temperature Compensation | 300 | 10 | 3000
Power Button | 1 | 10 | 10
LED | 0.5 | 10 | 5
|  | Subtotal | 15057.5
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Interns | 1250 | 2 | 2500
0
0
0
0
0
0
0
0
0
|  | Subtotal | 2500
Project Budget per F&S
Mounting | 500 | 10 | 5000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 5000
General Supplies & Other
Mounting Equipment | 15 | 10 | 150
Tag Distribution Packaging | 2.5 | 1000 | 2500
0
0
0
0
0
0
0
0
|  | Subtotal | 2650
|  | TOTAL BUDGET | 25207.5
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
Although we do not have hard data, this project ecourages biking. If more people bike, there will be fewer cars, which will reduce the amount of carbon dioxide emitted on campus.
End of Application