## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Friday Forum: Elevating Environmental Issues in Fall 2017
Total Amount Requested from SSC: | 30000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Draft Initial Speaker Ideas | 0 |  | Completed: March 25, 2017
Make initial contact to Bill McKibben, Indigenous Youth Council | 0 |  | Completed: March 6, 2017
Apply to Student Cultural Programs Fee | 2 |  | 2017-04-19
Solicit additional feedback on proposed speakers and speaker ideas from potential campus partners | 3 |  | 2017-05-06
Confirm funding for keynote speakers | 5 |  | 2017-05-01
Finalize speaker schedule | 5 |  | 2017-07-01
Solicit sponsorships from departments | 7 |  | 2017-07-30
Coordinate student organizations to table at speaker events | 4 |  | 2017-09-08
Coordinate engagement opportunities with students, departments and units | 4 |  | 2017-09-08
Develop and distribute series marketing | 6 |  | 2017-09-25
Speaking Engagements held on campus | 10 |  | 2017-12-15
Program Evaluation and Impact Assessed | 12 |  | 2017-12-20
Completion Report Submitted | 12 |  | 2017-12-20
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Honorarium: Bill McKibben | 25000 | 1 | 25000
Honorarium: Indigenous Youth Council | 5000 | 1 | 5000
0
0
0
0
0
0
0
0
|  | Subtotal | 30000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 30000
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
DiversityEd plans to apply for the Student Cultural Programs Fee committee for support to provide free lunch to students who attend (when relevant). The University YMCA has committed $5,000 to support as many highly qualified and engaging speakers to come to the project as possible. Additional funding could be secured from sponsorships and partnerships across campus should this funding not be enough to complete the project.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
End of Application