## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Illini EcoConcept: Designing and Fabricating a Fuel Cell-Driven Vehicle for the Shell Eco-Marathon Competition
Total Amount Requested from SSC: | 37056.38
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) - excl. breaks |  | Estimated Completion Date
Building chassis-related components | 5 |  | 2016-02-04
Machine body molds | 5 |  | 2016-02-04
Assembling suspension and brake components | 6 |  | 2016-02-11
Assembling steering components | 7 |  | 2016-02-18
Manufacture carbon fiber body panels | 7 |  | 2016-02-18
Build electronic throttle control system | 7 |  | 2016-02-18
Assemble drivetrain components in trailing arms | 7 |  | 2016-02-18
Assemble auxiliary electrical system | 9 |  | 2016-03-04
Chassis durability testing | 9 |  | 2016-03-04
Paint body panels & manufacture windows | 9 |  | 2016-03-04
Show vehicle to public for the 1st time in EOH | 10 |  | 2016-03-10
Vehicle testing and iterating | 15 |  | 2016-04-22
Compete in Shell Eco-Marathon Americas 2017 | 16 |  | 2016-04-27
Final Report | 18 |  | 2016-05-12
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Chassis
Motorcycle Brake Set | 293.64 | 1 | 293.64
Emergency break | 40 | 1 | 40
Trailing arm steel sheet | 100.62 | 2 | 201.24
Welding the chassis (Machine Shop) | 1200 | 2 | 2400
Machining chassis & steering components (Machine Shop) | 550 | 1 | 550
Using waterjet | 600 | 1 | 600
Electronics
Windows Surface Tablet | 500 | 1 | 500
Arduinos | 40 | 2 | 80
DC-DC 12V-5V converters | 3 | 20 | 60
Capacitor Bank | 2000 | 1 | 2000
Wire, Switches, PCB printing and relays | 450 | 1 | 450
Body
Carbon Fiber for the Body | 249.95 | 8 | 1999.6
VARTM Supplies (tubing, resin, dispertion medium, release film, vacuum bagging, sealant tape) | 1000 | 1 | 1000
Respirator Cartridges | 20 | 10 | 200
Mold Foam | 25 | 48 | 1200
Mold Sealant | 12 | 5 | 60
Mold Machining | 15000 | 1 | 15000
Plywood for Mold Structure | 500 | 1 | 500
Sandpaper | 15 | 4 | 60
Polycarbonate sheets | 25 | 3 | 75
3D Printing Light Housings | 120 | 4 | 480
Paint / Vinyl Wrap | 400 | 1 | 400
Metal for Hinges | 100 | 1 | 100
Thermoforming Windows | 1000 | 3 | 3000
Paint Guns | 40 | 2 | 80
Dremel Tool Cutting Disks | 19.99 | 10 | 199.9
Powertrain
Gearing | 50 | 2 | 100
Drivetrain Components (chain etc.) | 200 | 1 | 200
Motors | 500 | 2 | 1000
Controllers | 450 | 2 | 900
Controls Wiring/electrical components | 475 | 1 | 475
Fuel Cell Tubing | 200 | 1 | 200
Fuel Mounting | 100 | 1 | 100
Machining | 550 | 1 | 550
Fasteners | 10 | 5 | 50
|  | Subtotal | 35104.38
Publicity & Communication
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
|  | Subtotal | 0
General Supplies & Other
Hotel room for 3 nights of competition in April | 300 | 4 | 1200
U-Haul for competition (800 mi. total) | 752 | 1 | 752
|  | Subtotal | 1952
|  | TOTAL BUDGET | 37056.38
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Engineering Design Council ($5,000); Intren ($4,000); John Deere ($3,250); MechSE Student Society ($2,250); ECE Dept. ($1,500); TW Metals (~$1,250), SORF ($873.92); Maxon (~$1,500); Wilwood (~$100); Misumi (~$50)
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
End of Application