## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Sonified Sustainability Festival 2017 – a celebration of ecological music and arts
Total Amount Requested from SSC: | 35000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Successful Grant Funding would start early May 2016
Student Interns hired August/Sept 2016 (10 hours a week) | 7 weeks: August - October 1, 2016 |  | 2016 Oct 15
develop event management and promotion plans with interns | 11 weeks: October – December 15, 2016 |  | 2016 Dec 15
Employment period for paid student interns (10 hours a week) | 37 weeks: September 2016 – May 15, 2017 |  | 2017 May 15
Co-sponsored Performance 1 (Sudden Sound) Fall 2016/Spring 2017 | 30 weeks: September 2016 - April 2017 |  | 2017 April 30
2017 Sonified Sustainability Fest programming | 36 weeks: September 2016 - May 2017 |  | 2017 May 15
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
12x18 Posters (color printing , 1 side, recycled paper) | 1.1 | 500 | 550
Print ads - News Gazette | 308 | 3 | 924
Print ads - Daily Illini | 150 | 6 | 900
Digital ads - Inside Illinois | 350 | 2 | 700
Radio Underwriting Announcements - WILL 90.9FM | 18 | 15 | 270
Radio Underwriting Announcements - WEFT 90.1FM | 10 | 25 | 250
Documentation: two camera, location video ($75 per hour) | 75 | 12 | 900
Documentation: post-production ($50 per hour) | 50 | 32 | 1600
0
0
|  | Subtotal | 6094
Personnel & Wages
SSF 2017 Artist Fees | 10000 | 1 | 10000
Paid Student Intern - Events Management and Promotion | 8.5 | 900 | 7650
KCPA Event Staff (8 personel @ $15 per hour = $120) | 120 | 9 | 1080
SOM Audio Staff (Live music and film screening) | 200 | 1 | 200
0
0
0
0
0
0
|  | Subtotal | 18930
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
KCPA Facility Fees (University rate and table set up) | 1500 | 1 | 1500
Spurlock Facility Fees (4 hours) | 710 | 2 | 1420
Art Station Supplies | 500 | 1 | 500
sound equipment | 1500 | 1 | 1500
Art Exhibition expenses | 5000 | 1 | 5000
15-passenger van rental (transportation for sound walk locations) | 75 | 8 | 600
Screening fees | 250 | 2 | 500
Artist Transportation from NYC | 700 | 2 | 1400
Artist hotel accommdations | 140 | 14 | 1960
0
|  | Subtotal | 14380
|  | TOTAL BUDGET | 39404
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Krannert Center has pledged $5000.00 towards Sonified Sustainabilty Festival 2017 (see attached support letter) and Krannert Art Museum will sustain its programming support for the Sudden Sound Concert engagement. We plan to seek funding from other campus sources, including the Lorado Taft Arts Lectureship Fund and/or MillerComm to support the Walter Kitindu engagement.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
End of Application