## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Zero Waste Coordination
Total Amount Requested from SSC: | 75062
Amount Requested as: | grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Campus wide infrastructure - finalize bin locations |  |  | summer 2016
Campus wide infrastructure - order new bins |  |  | fall 2016
Campus wide infrastructure - install bins |  |  | spring 2016
Campus wide education - develop materials |  |  | summer 2016
Campus wide education - distribute messages |  |  | fall 2016 and spring 2017
Building Specific Solutions - collaborate on steps to take |  |  | fall 2016
Building Specific Solutions - implement selected changes |  |  | winter 2016
Building Specific Solutions - review changes for success |  |  | spring 2017
Special Recyclables - hire student employees |  |  | summer 2016
Special Recyclables - expand the programs |  |  | fall 2016 and spring 2017
Complete final report |  |  | 2017-05-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
new bins for North of Green Street | 650 | 25 | 16250
new bins for East of Quad | 650 | 10 | 6500
sand blasting and painting lids | 2500 | 2 | 5000
transporting bins to North of Green Street | 1000 | 1 | 1000
transporting bins to East of Quad | 1000 | 1 | 1000
0
0
0
0
0
|  | Subtotal | 29750
Publicity & Communication
Digital signage ad space, cost per location | 1800 | 4 | 7200
MTD cab cards printing | 1200 | 5 | 6000
0
0
0
0
0
0
0
0
|  | Subtotal | 13200
Personnel & Wages
Building specific solutions - ISTC coordination | 3440 | 8 | 27520
Special Recyclables - student employees | 17.8 | 200 | 3560
Educational Presentations by ISTC | 129 | 8 | 1032
0
0
0
0
0
0
0
|  | Subtotal | 32112
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 75062
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
F&S will contribute in-kind support for this program, through using administrative time for operational discussions and providing the support of the Superintendent of Grounds at no cost to the project budget.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
According to the iCAP greenhouse gas emissions inventory, reduced landfill waste does not reduce the campus GHG emissions.
End of Application