## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Sustainable Agricultural Food System - Grain Milling
Total Amount Requested from SSC: | 248832
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Receive Funding |  |  | Spring 2016
Harvest First Small Crop of Wheat - Collect Test Samples |  |  | 2016-07-01
Purchase Equipment |  |  | 2016-10-01
Plant Full Crop of Wheat |  |  | 2016-10-15
Install Equipment |  |  | 2017-01-01
Process Initial Batch of Flour - Small Test Samples |  |  | 2017-03-01
Trial Recipes With Fresh, Local Flour |  |  | 2017-06-01
Harvest First Full Crop of Wheat |  |  | 2017-07-01
Process First Full Crop of Wheat into Flour |  |  | 2017-10-01
Repeat process of planting, processing, and improving… |  |  | ongoing…
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Grain Cleaning Equipment | 15000 | 1 | 15000
Grain Milling Equipment | 45342 | 1 | 45342
Flour Packaging Equipment | 55000 | 1 | 55000
Test Baking Ovens | 18000 | 1 | 18000
Analytical Equipment for Safety & Quality Inspection | 97543 | 1 | 97543
Support Equipment for Product Development | 15947 | 1 | 15947
0
0
0
0
|  | Subtotal | 246832
Publicity & Communication
Costs of Marketing project at UIUC Dining Service (Dining Halls) is covered | 0 | 1 | 0
covered by UIUC Dining Services. Other online marketing | 0 | 1 | 0
planned does not have associated costs. Planned tours | 0 | 1 | 0
and printed article distribution will be included with | 0 | 1 | 0
other activities already covered by FSHN. | 0 | 1 | 0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Costs of student internships covered by UIUC | 0 | 1 | 0
Dining Services | 0 | 1 | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
N/A - All equipment to be installed in FSHN Pilot Plant, a | 0 | 1 | 0
plug and play facility. | 0 | 1 | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Start-Up Order of Bags for Final Packaging | 2000 | 1 | 2000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 2000
|  | TOTAL BUDGET | 248832
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
N/A
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
It would be difficult to calculate an exact savings without having extensive knowledge of the current supplier's supply chains, but it is apparent the GHG savings from the reduction in gasoline use will be substantial. The flour produced on campus will travel no more than 5 miles from farm to consumption, compared with hundreds or thousands of miles with the current suppliers.
End of Application